## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 18
PROJECT NAME | SLACK AND MSTEAMS INTEGRATION TO UEXCELERATE
PROJECT MENTOR (sponsor) | MR BHIBHU SAHOO
TEAM MEMBERS | AYUSH SHETA
ARYAN CHAUDHARY
JOSHITA DHANIREDDY
PRAJNA PENMETSA
ATHARV JOHAR

## Status
PROJECT NUMBER | 18
PROJECT NAME | SLACK BOT
PROJECT MENTOR (sponsor) | AGRIM
GIT Repository link : | https://github.com/DASS-Spring-2025/dass-spring-2025-project-team-18.git
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | Ayush , Aryan ,Prajna ,Atharv ,Joshita | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
GIT Repository setup | Preparation | Ayush , Aryan ,Prajna ,Atharv ,Joshita | 1 | 1.5 | Done |  | -0.5 | 33.3333
Client meeting 1 | Coordination | Ayush , Aryan ,Prajna ,Atharv ,Joshita | 1.5 | 1 | Done |  | 0.5 | 50
MOM-1 | Documentation | Prajna | 0.75 | 0.5 | Done | on github | 0.25 | 50
Requirement Doc | Requirements | Ayush | 2 | 1.5 | Ongoing | live document, iterated weekly based on client feedback , avialaible on github projectplan milestone , projectproposal | 0.5 | 33.3333
Research existing technology | Preparation | Ayush | 2 | 4 | Done | Briefing on Uexcelerate and chatbot integration in Slack & Teams, exploring their SDKs DOCUMENTATIONS | -2 | 50
Project synopsis writeup | Documentation | Prajna | 2 | 2 | Done |  | 0 | 0
Identify role owners | Preparation | Ayush | 1 | 0.6 | Done | roles assigned, balancing work across team members. Will adjust if needed. roles given in prjectplan uploaded to github | 0.4 | 66.6667
Team Meeting | Coordination | Atharv | 1.5 | 2 | Done | Intro meet and basic requiremnets discussed | -0.5 | 25
Status tracker | Documentation | Aryan | 1 | 1.5 | Done |  | -0.5 | 33.3333
going through doc and requirements | Requirements | Ayush , Aryan ,Prajna ,Atharv ,Joshita | 2 | 3 | Done | Team went over everything in detail, some areas need clarification from the client. | -1 | 33.3333
Week 2 (January 22 - January 28)
Finalize tech stack | Design | Ayush , Joshita | 2 | 3 | Done | Node.js, Slack SDK, MS Bot Framework finalized,Works well with our needs. | -1 | 33.3333
Create Slack workspace for communication with client | Coordination | Prajna | 0.5 | 1 | Done |  | -0.5 | 50
Client Meeting 2 | Coordination | Ayush , Aryan ,Prajna ,Atharv ,Joshita | 1 | 1 | Done | More clarity on expected chatbot functionalities. Some changes requested in the requirement file .. | 0 | 0
MOM-2 | Documentation | Joshita | 0.5 | 0.5 | Done | on github | 0 | 0
Learn Slack SDK, APIs: Preparation | Preparation | Ayush,Aryan | 5 | 4 | Done | Read official docs, watched YT tutorials, and tested basic commands. Need more hands-on work. | 1 | 25
Learn Node.js fundamentals | Preparation | Ayush , Aryan ,Prajna ,Atharv ,Joshita | 10 | 12 | Done | Working through tutorials , Pocs etc (all learned coz important for any part of project) -Everyone gained a solid foundation for the project. | -2 | 16.6667
Team Meeting | Coordination | Ayush , Aryan ,Prajna ,Atharv ,Joshita | 1 | 1 | Done | Discussed findings from Slack SDK and tech stack decisions and future plans acc to meeting 2 | 0 | 0
Status tracker | Documentation | Ayush | 1 | 0.75 | Done |  | 0.25 | 33.3333
Client Meeting 3 | Coordination | Ayush , Aryan ,Prajna ,Atharv ,Joshita | 1 | 1 | Done |  | 0 | 0
MOM-3 | Documentation | Ayush | 0.5 | 1 | Done | on github | -0.5 | 50
Develop Proof of Concept (POC): Slack Bot (Command Handling, No API) | Development | Ayush,Aryan | 3 | 5 | Done | Basic sample bot responding to commands (uploaded to github) | -2 | 40
Develop POC: Slack Bot (Message Handling, No API Integration) | Development | Ayush,Aryan | 3 | 3 | Done | Implementing message parsing & response logic and making similar bot as command (uploaded to github) | 0 | 0
Week 3 (January 29 - February 4)
Week 4
Week 5
Week 6
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on D25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2*5
Note on E25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2,2,3,3,2
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically